## Dashboard
Valaiyagam E-Commerce — Project Tracking Dashboard
Project | Valaiyagam Admin + Fashion Shopping (full sync)
Start Date | 2026-07-14
Planned End | 2026-11-01
Document Date | 2026-07-25
Architecture | Admin :3000/:8000 · Shopping :3001/:8001 · PostgreSQL shared DB
KPI | Value
Total Stories (VL + VS) | 60
Foundation stories (VL-*) | 32
Shopping sync stories (VS-*) | 28
Done | 51
In Progress | 8
Planned | 1
% Complete | 85%
How to use this workbook
1. Update Stories sheet status weekly (Done / In Progress / Planned / Blocked).
2. Use E2E Workflows sheet for admin↔shopping reflection scenarios (WF-A to WF-F).
3. Create Git branch using the exact name in column Git Feature / Branch.
4. Link PRs to Story ID (example: VS-018) in the PR title.
5. Review Timeline sheet in client weekly calls (P* + S* phases).
6. Use Dev Workflow sheet as Definition of Done checklist.
7. Run docs/UAT_CHECKLIST_SHOPPING.md for publish→buy→fulfill sign-off.
8. Plan details: docs/SHOPPING_ADMIN_WORKFLOW_PLAN.md
Related docs
docs/SHOPPING_ADMIN_WORKFLOW_PLAN.md
docs/UAT_CHECKLIST_SHOPPING.md
docs/ECOM_ARCHITECTURE_AND_TIMELINE.md
docs/architecture/system-architecture.md
docs/api/api-documentation.md

## Stories
ID | Date | Phase | Week | Module | Story Title | User Story | Git Feature / Branch | Branch Type | Priority | Status | Owner | Estimate (Days) | Depends On | Acceptance Criteria | Notes
VL-001 | 2026-07-13 | P0 Foundation | 1 | Platform | Project bootstrap & Docker network | As a developer, I can run the full stack with docker compose so local setup is consistent. | feat/platform-docker-compose | feat | P0 | Done | Backend | 2 | - | Compose brings up postgres, admin/shopping backends and frontends | PostgreSQL network
VL-002 | 2026-07-13 | P0 Foundation | 1 | Backend | Layered FastAPI structure | As a developer, I have model/schema/repository/service/route layers for maintainable APIs. | feat/backend-layered-structure | feat | P0 | Done | Backend | 2 | VL-001 | Folders and imports follow agreed architecture | Modular monolith
VL-003 | 2026-07-13 | P0 Foundation | 1 | Auth | JWT login + Argon2 passwords | As an admin, I can securely sign in and receive an access token. | feat/auth-jwt-login | feat | P0 | Done | Backend | 2 | VL-002 | Login returns token; invalid credentials rejected | OAuth2 password form
VL-004 | 2026-07-13 | P0 Foundation | 1 | RBAC | Default roles seed (admin/manager/viewer) | As the system, I seed default roles and an initial admin user on first boot. | feat/rbac-default-roles-seed | feat | P0 | Done | Backend | 1 | VL-003 | admin/manager/viewer exist; initial admin can login | Credentials via env
VL-005 | 2026-07-20 | P0 Foundation | 2 | Users | User CRUD APIs | As an admin, I can create, list, update, and delete users with role assignment. | feat/users-crud-api | feat | P0 | Done | Backend | 2 | VL-004 | All CRUD endpoints work with RBAC guards | Admin-only write
VL-006 | 2026-07-20 | P0 Foundation | 2 | Roles | Role CRUD APIs | As an admin, I can manage custom roles while system roles stay protected. | feat/roles-crud-api | feat | P0 | Done | Backend | 1 | VL-004 | Cannot delete/rename protected roles unsafely | Name update supported
VL-007 | 2026-07-20 | P0 Foundation | 2 | Frontend | Light glass admin shell + Redux store | As an admin, I use a light glassmorphism UI with Redux-managed auth/users/roles. | feat/admin-glass-ui-redux | feat | P0 | Done | Frontend | 3 | VL-005 | Login + dashboard match UI standards | No dark theme
VL-008 | 2026-07-20 | P0 Foundation | 2 | Frontend | User/Role edit modals + confirm delete | As an admin, I can edit users/roles in modals and must confirm deletes. | feat/admin-edit-confirm-modals | feat | P0 | Done | Frontend | 2 | VL-007 | Edit works; delete uses ConfirmDialog | Mobile responsive cards
VL-009 | 2026-07-20 | P0 Foundation | 2 | Database | PostgreSQL schema + Alembic migrations | As a developer, schema changes are versioned with Alembic on PostgreSQL. | feat/alembic-postgresql-schema | feat | P0 | Done | Backend | 2 | VL-002 | alembic upgrade head creates core tables | Migrated from MySQL
VL-010 | 2026-07-27 | P1 Catalog | 3 | Catalog | Category CRUD | As an admin, I can create and organize product categories. | feat/catalog-categories | feat | P1 | Done | Backend | 3 | VL-009 | Nested or flat categories with active flag | Admin UI live
VL-011 | 2026-07-27 | P1 Catalog | 3 | Catalog | Product create/edit with media | As an admin, I can publish products with images, price, and description. | feat/catalog-products-media | feat | P1 | Done | Fullstack | 5 | VL-010 | Product visible in admin list; media upload works | Local uploads volume
VL-012 | 2026-08-03 | P1 Catalog | 4 | Catalog | Product variants (size/color) | As an admin, I can define variants with SKU and price overrides. | feat/catalog-product-variants | feat | P1 | Done | Backend | 4 | VL-011 | Variants persist and appear in product detail | JSON options
VL-013 | 2026-08-03 | P1 Catalog | 4 | Inventory | Stock levels & low-stock alerts | As a manager, I can monitor stock and get low-stock warnings. | feat/inventory-stock-alerts | feat | P1 | Done | Fullstack | 4 | VL-012 | Stock updates on admin; alert threshold configurable | Inventory panel
VL-014 | 2026-08-10 | P1 Catalog | 5 | Storefront | Public catalog browse & product detail | As a customer, I can browse products and open product details. | feat/storefront-catalog-browse | feat | P1 | Done | Frontend | 5 | VL-011 | Listing + detail pages responsive | Shopping + admin /store
VL-015 | 2026-08-17 | P2 Orders | 6 | Cart | Cart add/update/remove | As a customer, I can manage cart items before checkout. | feat/cart-management | feat | P1 | Done | Fullstack | 4 | VL-014 | Guest + logged-in cart supported | Shopping cart API
VL-016 | 2026-08-17 | P2 Orders | 6 | Checkout | Address book & shipping quote | As a customer, I can select delivery address and see shipping estimate. | feat/checkout-address-shipping | feat | P1 | Done | Fullstack | 5 | VL-015 | Address validation + quote returned | Customer addresses
VL-017 | 2026-08-24 | P2 Orders | 7 | Orders | Create order lifecycle APIs | As the system, I create orders with line items and status machine. | feat/orders-lifecycle-api | feat | P0 | Done | Backend | 5 | VL-016 | Statuses pending/paid/cancelled/return supported | Shared orders table
VL-018 | 2026-08-31 | P2 Orders | 8 | Admin | Admin order list & detail | As an admin, I can view and filter orders with line-item detail. | feat/admin-orders-console | feat | P1 | Done | Frontend | 4 | VL-017 | Filters by status/date; detail shows totals | OrdersPanel
VL-019 | 2026-09-07 | P3 Payments | 9 | Payments | Razorpay order + checkout SDK | As a customer, I can pay for an order via Razorpay checkout. | feat/payments-razorpay-checkout | feat | P0 | In Progress | Fullstack | 5 | VL-017 | Sandbox payment succeeds and maps to order | Demo provider + real wiring
VL-020 | 2026-09-07 | P3 Payments | 9 | Payments | Payment webhook + signature verify | As the system, I verify gateway webhooks and update payment status idempotently. | feat/payments-razorpay-webhook | feat | P0 | In Progress | Backend | 4 | VL-019 | Invalid signature rejected; duplicate events ignored | Demo signature gate
VL-021 | 2026-09-14 | P3 Payments | 10 | Payments | Refunds & COD flow | As an admin, I can refund paid orders; customers can choose COD where allowed. | feat/payments-refunds-cod | feat | P1 | Done | Fullstack | 4 | VL-020 | Partial/full refund + COD order path verified | COD path live
VL-022 | 2026-09-21 | P4 Courier | 11 | Courier | Courier adapter interface | As a developer, I can plug multiple courier partners behind one service contract. | feat/courier-adapter-interface | feat | P0 | Done | Backend | 3 | VL-021 | create/cancel/track/label methods defined | Manual adapter included
VL-023 | 2026-09-21 | P4 Courier | 11 | Courier | Shiprocket/Delhivery shipment create | As an ops user, I can create a shipment and receive an AWB for a paid order. | feat/courier-create-shipment-awb | feat | P0 | In Progress | Backend | 5 | VL-022 | AWB saved on shipment; label URL available | Needs partner credentials
VL-024 | 2026-09-28 | P4 Courier | 12 | Courier | Label print & pickup scheduling | As warehouse staff, I can print labels and schedule pickups. | feat/courier-labels-pickup | feat | P1 | In Progress | Fullstack | 4 | VL-023 | Label downloadable; pickup confirmation stored | Shipments panel
VL-025 | 2026-10-05 | P5 Tracking | 13 | Tracking | Shipment event ingestion | As the system, I ingest courier webhooks/polls into shipment_events. | feat/tracking-shipment-events | feat | P0 | Done | Backend | 4 | VL-023 | Timeline events ordered by timestamp | Admin events API
VL-026 | 2026-10-05 | P5 Tracking | 13 | Tracking | Customer order tracking page | As a customer, I can track my order with a clear status timeline. | feat/tracking-customer-timeline-ui | feat | P0 | In Progress | Frontend | 4 | VL-025 | Shows Placed→Delivered stages with AWB | Wire shipment events next
VL-027 | 2026-10-12 | P5 Tracking | 14 | Notify | Order/shipment notifications | As a customer, I receive email/SMS updates for payment and shipment milestones. | feat/notifications-order-shipment | feat | P1 | In Progress | Backend | 4 | VL-026 | Templates for paid/shipped/delivered | Admin send exists; delivery TBD
VL-028 | 2026-10-12 | P5 Tracking | 14 | Admin | Exception queue & manual override | As ops, I can manage delayed/RTO shipments and log manual overrides. | feat/tracking-exception-queue | feat | P1 | Done | Fullstack | 3 | VL-025 | Override requires reason; audited | Exceptions panel
VL-029 | 2026-10-19 | P6 Launch | 15 | Reports | Sales & fulfillment dashboard | As a business owner, I can view sales, payment, and delivery KPIs. | feat/reports-sales-fulfillment | feat | P1 | Done | Fullstack | 4 | VL-021 | Daily/weekly charts and CSV export | Reports panel
VL-030 | 2026-10-19 | P6 Launch | 15 | QA | UAT script & bugfix sprint | As the client, I can execute UAT and log defects against stories. | fix/uat-bugfix-pass | fix | P0 | In Progress | QA | 5 | VL-027 | Critical bugs closed; UAT sign-off recorded | Shopping UAT added
VL-031 | 2026-10-26 | P6 Launch | 16 | Ops | Staging → production cutover | As the team, we deploy production with migrations, secrets, and monitoring. | feat/prod-cutover-checklist | feat | P0 | Planned | DevOps | 3 | VL-030 | HTTPS, backups, smoke tests green | Postgres cutover
VL-032 | 2026-10-26 | P6 Launch | 16 | Docs | Client runbook & training | As the client ops team, I have a runbook for daily admin tasks. | docs/client-ops-runbook | docs | P2 | In Progress | PM | 2 | VL-031 | Runbook covers users, orders, refunds, shipments | Update for shopping
VS-001 | 2026-08-10 | S1 Theme | 5 | Shopping UI | Fashion theme baseline (BlueBerry) | As a shopper, I see a fashion-ready Valaiyagam storefront using the BlueBerry theme. | feat/vs-001-fashion-theme-baseline | feat | P0 | Done | Frontend | 3 | VL-014 | Theme loads on :3001; brand renamed Valaiyagam Fashion | shopping/frontend
VS-002 | 2026-08-10 | S1 Theme | 5 | Shopping UI | Header/footer categories from API | As a shopper, navigation categories come from admin-managed categories. | feat/vs-002-nav-categories-api | feat | P0 | Done | Frontend | 2 | VS-001 | Header/menu uses GET /categories; empty state handled | Replace static chips
VS-003 | 2026-08-10 | S1 Theme | 5 | Shopping UI | Remove static catalog fallback | As an admin, unpublished/empty catalog is not masked by demo static products. | feat/vs-003-api-only-catalog | feat | P0 | Done | Frontend | 2 | VS-001 | Shop/home show empty state when API returns zero published products | Critical for UAT honesty
VS-004 | 2026-08-10 | S2 Catalog Sync | 5 | Catalog Sync | Admin publish reflects on shopping | As an admin, when I publish a product it appears on the shopping site without redeploy. | feat/vs-004-publish-reflects-shopping | feat | P0 | Done | Fullstack | 3 | VL-011 | is_published+public+active product visible on /shop and PDP within refresh | Shared products table
VS-005 | 2026-08-10 | S2 Catalog Sync | 5 | Catalog Sync | Category sync to shop filters | As a shopper, I can filter products by admin categories and subcategories. | feat/vs-005-category-filter-sync | feat | P0 | Done | Fullstack | 2 | VL-010 | GET /categories and category products match admin tree | -
VS-006 | 2026-08-17 | S2 Catalog Sync | 6 | Catalog Sync | Product media gallery sync | As a shopper, I see admin-uploaded images on the product gallery. | feat/vs-006-media-gallery-sync | feat | P0 | Done | Fullstack | 2 | VL-011 | Primary + gallery images load from /uploads via shopping API origin | -
VS-007 | 2026-08-17 | S2 Catalog Sync | 6 | Catalog Sync | Size/color variants on shopping | As a shopper, I select size/color variants created in admin before add-to-cart. | feat/vs-007-variant-selection | feat | P0 | Done | Fullstack | 3 | VL-012 | Variant SKU/stock enforced; filters size/color work on listing | -
VS-008 | 2026-08-17 | S2 Catalog Sync | 6 | Catalog | Brand CRUD in admin + shop filter | As an admin, I manage brands; shoppers filter by brand on shopping. | feat/vs-008-brand-admin-crud | feat | P1 | Done | Fullstack | 3 | VS-004 | Admin Brands panel; product brand_id; GET /brands used in shop | Gap today
VS-009 | 2026-08-17 | S2 Catalog Sync | 6 | Catalog | Merchandising flags UI | As an admin, I mark products featured/trending/best-seller for shopping home tabs. | feat/vs-009-merchandising-flags-ui | feat | P1 | Done | Fullstack | 2 | VS-004 | Admin form toggles flags; shopping featured/trending/best-sellers endpoints return them | Flags exist in DB
VS-010 | 2026-08-24 | S2 Catalog Sync | 7 | Shopping API | Live search & suggestions | As a shopper, search and typeahead use the live published catalog. | feat/vs-010-search-suggestions | feat | P1 | Done | Fullstack | 2 | VS-004 | GET /products/search and /suggestions return admin products only | -
VS-011 | 2026-08-24 | S3 Commerce | 7 | Auth | Customer register/login/refresh | As a customer, I can register, login, refresh tokens, and logout securely. | feat/vs-011-customer-auth | feat | P0 | Done | Fullstack | 3 | VL-003 | JWT access+refresh; /auth/me works; tokens stored securely on client | customers table
VS-012 | 2026-08-24 | S3 Commerce | 7 | Cart | Guest cart merge after login | As a customer, my guest cart merges into my account cart after login. | feat/vs-012-guest-cart-merge | feat | P0 | Done | Fullstack | 2 | VS-011 | POST /cart/merge combines lines; no duplicate variants | -
VS-013 | 2026-08-31 | S3 Commerce | 8 | Engagement | Wishlist & compare theme pages | As a shopper, I can wishlist and compare products using theme pages backed by APIs. | feat/vs-013-wishlist-compare | feat | P1 | Done | Fullstack | 3 | VS-011 | Wishlist/compare persist for logged-in users; max 4 compare items | -
VS-014 | 2026-08-31 | S3 Commerce | 8 | Checkout | Customer address book | As a customer, I manage multiple addresses and set a default for checkout. | feat/vs-014-address-book | feat | P0 | Done | Fullstack | 2 | VS-011 | CRUD + PUT default; addresses scoped to customer_id | -
VS-015 | 2026-08-31 | S3 Commerce | 8 | Checkout | Checkout preview/validate/create-order | As a customer, I can preview totals and place an order from my cart. | feat/vs-015-checkout-create-order | feat | P0 | Done | Fullstack | 4 | VS-014 | POST /checkout/* creates order with line snapshots and shipping fields | -
VS-016 | 2026-09-07 | S3 Commerce | 9 | Coupons | Coupon apply/remove on shopping cart | As a customer, I can apply/remove admin coupons and see discount on checkout. | feat/vs-016-coupon-cart-persist | feat | P1 | Done | Fullstack | 2 | VS-015 | Coupon stored on cart; validate min/max/expiry; usage recorded on order | -
VS-017 | 2026-09-07 | S3 Commerce | 9 | Payments | COD + Razorpay create/verify from shopping | As a customer, I can pay COD or via gateway; payment records are created. | feat/vs-017-shopping-payments | feat | P0 | Done | Fullstack | 4 | VS-015 | Payments appear for admin; COD stays pending until mark-paid | Demo provider
VS-018 | 2026-09-07 | S4 Admin Reflect | 9 | Orders Sync | Shopping order visible in Admin Orders | As an admin, every shopping-placed order appears in the Orders panel immediately. | feat/vs-018-order-admin-reflect | feat | P0 | Done | Fullstack | 2 | VS-015 | Filter/search finds order_number; detail shows customer_id lines and totals | Shared orders table
VS-019 | 2026-09-14 | S4 Admin Reflect | 10 | Orders Sync | Admin mark-paid/cancel updates shopping | As a customer, admin mark-paid/cancel is reflected when I fetch order/tracking. | feat/vs-019-admin-status-to-shopping | feat | P0 | Done | Fullstack | 2 | VS-018 | GET /orders/{id} and tracking show updated status_history | -
VS-020 | 2026-09-14 | S4 Admin Reflect | 10 | Inventory Sync | Checkout reserves admin inventory | As ops, shopping checkout reserves/deducts stock visible in Inventory panel. | feat/vs-020-inventory-reserve-sync | feat | P0 | Done | Backend | 3 | VL-013 | Stock movements created; oversell blocked when stock insufficient | -
VS-021 | 2026-09-14 | S4 Admin Reflect | 10 | Customers | Admin Customers console | As an admin, I can list/search/disable shopping customers and view their orders. | feat/vs-021-admin-customers-console | feat | P1 | Done | Fullstack | 4 | VS-011 | Customers tab with status toggle; link to orders | Gap today
VS-022 | 2026-09-21 | S4 Admin Reflect | 11 | Coupons | Coupon usage audit in admin | As an admin, I can see which customers used which coupons on which orders. | feat/vs-022-coupon-usage-audit | feat | P2 | Done | Fullstack | 2 | VS-016 | Admin view of coupon_usages with customer/order links | -
VS-023 | 2026-09-21 | S4 Admin Reflect | 11 | Reviews | Review moderation in admin | As an admin, I approve/reject product reviews submitted from shopping. | feat/vs-023-review-moderation | feat | P1 | Done | Fullstack | 3 | VS-007 | Only approved reviews show on PDP; admin panel lists pending | is_approved exists
VS-024 | 2026-09-28 | S5 Fulfillment | 12 | Tracking | Admin shipment → shopping track | As a customer, tracking shows admin shipment AWB and status events. | feat/vs-024-shipment-to-track | feat | P0 | Done | Fullstack | 4 | VL-025 | Track page merges order_status_history + shipment_events | Primary loop
VS-025 | 2026-09-28 | S5 Fulfillment | 12 | Orders | Full order status machine on shopping | As a customer, I can cancel/return/reorder and see statuses matching admin lifecycle. | feat/vs-025-order-status-machine | feat | P0 | Done | Backend | 3 | VS-018 | cancel/return/reorder/invoice endpoints work with auth | -
VS-026 | 2026-10-05 | S5 Fulfillment | 13 | Notify | Customer order notifications | As a customer, I receive notifications when order is paid/shipped/delivered. | feat/vs-026-customer-notifications | feat | P1 | Done | Backend | 4 | VS-024 | Email/SMS templates fired from status transitions | Provider TBD
VS-027 | 2026-10-12 | S6 Harden | 14 | Checkout | Tax rules from admin in shopping checkout | As a shopper, tax is calculated from admin tax rules during preview/create-order. | feat/vs-027-tax-rules-checkout | feat | P1 | Done | Backend | 3 | VS-015 | tax_amount > 0 when matching tax rule exists | Currently hardcoded 0
VS-028 | 2026-10-19 | S6 Harden | 15 | QA | E2E UAT publish→buy→fulfill→track→review | As the client, I can run a full admin↔shopping UAT script and sign off. | test/vs-028-shopping-admin-uat | fix | P0 | Done | QA | 5 | VS-024 | All workflow A–E steps pass; defects logged to stories | See UAT_CHECKLIST_SHOPPING.md

## E2E Workflows
Workflow ID | Name | Starts In | Ends In | Admin / Source Steps | Shopping / Target Steps | Linked Stories | Priority | Status
WF-A | Publish Product | Admin | Shopping | 1) Login admin 2) Create category 3) Create product+media+variants 4) Publish public 5) Set stock | 6) Open shopping home/shop 7) Find product 8) Open PDP 9) See images/variants/price | VS-004,VS-005,VS-006,VS-007 | P0 | Done
WF-B | Place Order | Shopping | Admin | 1) Register/login 2) Add variant to cart 3) Apply coupon 4) Address 5) Checkout COD/Razorpay | 6) Admin Orders shows order 7) Payments row exists 8) Inventory reserved | VS-011,VS-015,VS-016,VS-017,VS-018,VS-020 | P0 | Done
WF-C | Fulfill & Track | Admin | Shopping | 1) Mark paid 2) Create shipment+AWB 3) Add events packed/shipped/delivered | 4) Customer Track Order timeline updates 5) Optional notification | VS-019,VS-024,VS-025,VS-026 | P0 | Done
WF-D | Catalog Change | Admin | Shopping | 1) Edit price/image/stock or unpublish | 2) Shopping list/PDP reflects change on refresh; unpublished hidden | VS-003,VS-004,VS-006 | P1 | Done
WF-E | Coupon & Offer | Admin | Shopping | 1) Create coupon with rules in admin | 2) Apply on shopping cart/checkout 3) Order stores discount 4) Admin sees usage | VS-016,VS-022 | P1 | Done
WF-F | Review Loop | Shopping | Admin | 1) Delivered customer submits review+images | 2) Admin moderates 3) Approved review appears on PDP | VS-023 | P1 | Done

## Timeline
Phase | Week Start | Week End | Focus | Milestone | Exit Criteria | Status
P0 Foundation | 2026-07-13 | 2026-07-26 | Auth, RBAC, Docker, UI shell | M1 Foundation demo | Admin login + user/role CRUD | Done
P1 Catalog | 2026-07-27 | 2026-08-16 | Categories, products, inventory | M2 Catalog demo | Publish products to storefront | Done
P2 Orders | 2026-08-17 | 2026-09-06 | Cart, checkout, order lifecycle | M3 Checkout demo | Place order end-to-end | Done
P3 Payments | 2026-09-07 | 2026-09-20 | Gateway, webhooks, refunds, COD | M4 Payment demo | Paid order verified | In Progress
P4 Courier | 2026-09-21 | 2026-10-04 | Adapters, AWB, labels, pickup | M5 Courier demo | Shipment created from paid order | In Progress
P5 Tracking | 2026-10-05 | 2026-10-18 | Timeline UI + notifications | M6 Tracking demo | Customer can track order | In Progress
P6 Launch | 2026-10-19 | 2026-11-01 | Reports, UAT, production cutover | M7 Go-live | Production ready checklist | In Progress
S1 Theme | 2026-08-10 | 2026-08-23 | BlueBerry fashion theme + API nav | MS1 Theme live | Shopping UI on :3001 branded | Done
S2 Catalog Sync | 2026-08-10 | 2026-08-30 | Admin publish → shopping shelf | MS2 Catalog sync | Publish reflects on shop | Done
S3 Commerce | 2026-08-24 | 2026-09-13 | Auth, cart, checkout, payments | MS3 Buy path | Customer can place order | Done
S4 Admin Reflect | 2026-09-07 | 2026-09-27 | Orders/inventory/customers reflection | MS4 Ops loop | Admin sees shopping orders | Done
S5 Fulfillment | 2026-09-28 | 2026-10-11 | Shipment → customer track | MS5 Track loop | Track shows AWB/events | Done
S6 Harden | 2026-10-12 | 2026-11-01 | Tax, reviews, UAT, cutover | MS6 Sign-off | Full WF-A–F UAT passed | Done

## Git Branches
Branch Name | Type | Linked Story ID | Title | Target | Status
feat/platform-docker-compose | feat | VL-001 | Project bootstrap & Docker network | develop | Done
feat/backend-layered-structure | feat | VL-002 | Layered FastAPI structure | develop | Done
feat/auth-jwt-login | feat | VL-003 | JWT login + Argon2 passwords | develop | Done
feat/rbac-default-roles-seed | feat | VL-004 | Default roles seed (admin/manager/viewer) | develop | Done
feat/users-crud-api | feat | VL-005 | User CRUD APIs | develop | Done
feat/roles-crud-api | feat | VL-006 | Role CRUD APIs | develop | Done
feat/admin-glass-ui-redux | feat | VL-007 | Light glass admin shell + Redux store | develop | Done
feat/admin-edit-confirm-modals | feat | VL-008 | User/Role edit modals + confirm delete | develop | Done
feat/alembic-postgresql-schema | feat | VL-009 | PostgreSQL schema + Alembic migrations | develop | Done
feat/catalog-categories | feat | VL-010 | Category CRUD | develop | Done
feat/catalog-products-media | feat | VL-011 | Product create/edit with media | develop | Done
feat/catalog-product-variants | feat | VL-012 | Product variants (size/color) | develop | Done
feat/inventory-stock-alerts | feat | VL-013 | Stock levels & low-stock alerts | develop | Done
feat/storefront-catalog-browse | feat | VL-014 | Public catalog browse & product detail | develop | Done
feat/cart-management | feat | VL-015 | Cart add/update/remove | develop | Done
feat/checkout-address-shipping | feat | VL-016 | Address book & shipping quote | develop | Done
feat/orders-lifecycle-api | feat | VL-017 | Create order lifecycle APIs | develop | Done
feat/admin-orders-console | feat | VL-018 | Admin order list & detail | develop | Done
feat/payments-razorpay-checkout | feat | VL-019 | Razorpay order + checkout SDK | develop | In Progress
feat/payments-razorpay-webhook | feat | VL-020 | Payment webhook + signature verify | develop | In Progress
feat/payments-refunds-cod | feat | VL-021 | Refunds & COD flow | develop | Done
feat/courier-adapter-interface | feat | VL-022 | Courier adapter interface | develop | Done
feat/courier-create-shipment-awb | feat | VL-023 | Shiprocket/Delhivery shipment create | develop | In Progress
feat/courier-labels-pickup | feat | VL-024 | Label print & pickup scheduling | develop | In Progress
feat/tracking-shipment-events | feat | VL-025 | Shipment event ingestion | develop | Done
feat/tracking-customer-timeline-ui | feat | VL-026 | Customer order tracking page | develop | In Progress
feat/notifications-order-shipment | feat | VL-027 | Order/shipment notifications | develop | In Progress
feat/tracking-exception-queue | feat | VL-028 | Exception queue & manual override | develop | Done
feat/reports-sales-fulfillment | feat | VL-029 | Sales & fulfillment dashboard | develop | Done
fix/uat-bugfix-pass | fix | VL-030 | UAT script & bugfix sprint | develop | In Progress
feat/prod-cutover-checklist | feat | VL-031 | Staging → production cutover | develop | Planned
docs/client-ops-runbook | docs | VL-032 | Client runbook & training | develop | In Progress
feat/vs-001-fashion-theme-baseline | feat | VS-001 | Fashion theme baseline (BlueBerry) | develop | Done
feat/vs-002-nav-categories-api | feat | VS-002 | Header/footer categories from API | develop | Done
feat/vs-003-api-only-catalog | feat | VS-003 | Remove static catalog fallback | develop | Done
feat/vs-004-publish-reflects-shopping | feat | VS-004 | Admin publish reflects on shopping | develop | Done
feat/vs-005-category-filter-sync | feat | VS-005 | Category sync to shop filters | develop | Done
feat/vs-006-media-gallery-sync | feat | VS-006 | Product media gallery sync | develop | Done
feat/vs-007-variant-selection | feat | VS-007 | Size/color variants on shopping | develop | Done
feat/vs-008-brand-admin-crud | feat | VS-008 | Brand CRUD in admin + shop filter | develop | Done
feat/vs-009-merchandising-flags-ui | feat | VS-009 | Merchandising flags UI | develop | Done
feat/vs-010-search-suggestions | feat | VS-010 | Live search & suggestions | develop | Done
feat/vs-011-customer-auth | feat | VS-011 | Customer register/login/refresh | develop | Done
feat/vs-012-guest-cart-merge | feat | VS-012 | Guest cart merge after login | develop | Done
feat/vs-013-wishlist-compare | feat | VS-013 | Wishlist & compare theme pages | develop | Done
feat/vs-014-address-book | feat | VS-014 | Customer address book | develop | Done
feat/vs-015-checkout-create-order | feat | VS-015 | Checkout preview/validate/create-order | develop | Done
feat/vs-016-coupon-cart-persist | feat | VS-016 | Coupon apply/remove on shopping cart | develop | Done
feat/vs-017-shopping-payments | feat | VS-017 | COD + Razorpay create/verify from shopping | develop | Done
feat/vs-018-order-admin-reflect | feat | VS-018 | Shopping order visible in Admin Orders | develop | Done
feat/vs-019-admin-status-to-shopping | feat | VS-019 | Admin mark-paid/cancel updates shopping | develop | Done
feat/vs-020-inventory-reserve-sync | feat | VS-020 | Checkout reserves admin inventory | develop | Done
feat/vs-021-admin-customers-console | feat | VS-021 | Admin Customers console | develop | Done
feat/vs-022-coupon-usage-audit | feat | VS-022 | Coupon usage audit in admin | develop | Done
feat/vs-023-review-moderation | feat | VS-023 | Review moderation in admin | develop | Done
feat/vs-024-shipment-to-track | feat | VS-024 | Admin shipment → shopping track | develop | Done
feat/vs-025-order-status-machine | feat | VS-025 | Full order status machine on shopping | develop | Done
feat/vs-026-customer-notifications | feat | VS-026 | Customer order notifications | develop | Done
feat/vs-027-tax-rules-checkout | feat | VS-027 | Tax rules from admin in shopping checkout | develop | Done
test/vs-028-shopping-admin-uat | fix | VS-028 | E2E UAT publish→buy→fulfill→track→review | develop | Done

## Dev Workflow
Step | Stage | Owner | Input | Output | Tool / Gate
1 | Story drafted | PM | Client requirement | Story in Stories sheet | PROJECT_TRACKING.xlsx
2 | Branch created | Dev | Story ID + title | feat/fix branch | Git
3 | Implementation | Dev | Acceptance criteria | Code + tests | IDE / Docker
4 | Migration (if schema) | Backend | Model change | Alembic revision | alembic revision
5 | Pull request | Dev | Branch commits | PR to develop | GitHub/GitLab
6 | Code review | Peer | PR | Approved PR | Review checklist
7 | CI / smoke | CI | PR build | Green checks | Docker compose tests
8 | Merge | Maintainer | Approved PR | Updated develop | Protected branch
9 | UAT on staging | Client + QA | Build on staging | Pass/fail notes | UAT_CHECKLIST_SHOPPING.md
10 | Admin↔Shopping verify | QA | WF-A to WF-F | Reflection confirmed | E2E Workflows sheet
11 | Story status update | PM | UAT result | Status=Done | Excel tracker
12 | Release to main | DevOps | Stable develop | Production tag | Release checklist

## Integrations
Integration | Provider Options | Phase | Story IDs | Key Objects | Success Metric
Payments | Razorpay (primary), Stripe (optional), COD | P3 / S3 | VL-019, VL-020, VL-021, VS-017 | payments, payment_events, refunds | Paid order confirmed via verified webhook
Courier | Shiprocket / Delhivery / BlueDart + manual | P4 / S5 | VL-022, VL-023, VL-024, VS-024 | shipments, courier_accounts, labels | AWB created from paid order < 2 minutes
Tracking | Partner webhooks + internal timeline | P5 / S5 | VL-025, VL-026, VL-027, VL-028, VS-024, VS-025 | shipment_events, order_status_history, notifications | Customer sees live timeline with AWB
Catalog Sync | Shared PostgreSQL products/categories/media | S2 | VS-004, VS-005, VS-006, VS-007, VS-008, VS-009 | products, product_media, product_variants, brands | Admin publish visible on shopping without redeploy